## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-13-d temp
Testing Team Name | 2221-swen-261-03-team3

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | Sprint 3 - Our Team
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | SH - either the main page or back from the cart | Pass | CS - 11/3/2022
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | SH - either the main page or back from the cart | Pass | CS - 11/3/2022
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | SH - not really necessary | Pass | CS - 11/3/2022
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | SH - there is a detail view by clicking on the product | Pass | CS - 11/3/2022
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | SH | Pass | CS - 11/3/2022
As an Owner, I want to log into the admin account so that I can manage the store. | Given I am logging in when I use the "admin" username then I should be logged into the site with admin access. | Pass | SH | Pass | CS - 11/3/2022
As a customer, I want to log into the e-store so that I can use it as I wish | Given I am logging in when I provide my username then I should be logged into my account. | Pass | SH | Pass | CS - 11/3/2022
As a customer, I want to create a new account so that I can use the website | Given a login page when I create an account then I should be able to use the website. | Fail | SH - Not part of this sprint | Pass | CS - 11/3/2022
As a Customer, I want to remove items from my shopping cart so that I can not buy items. | Given an item when I remove it from the cart then it should be removed from the cart. | Pass | SH | Pass | CS - 11/3/2022
As a Customer I want to add items to my shopping cart so that I can buy items | Given an item when I add it to the shopping cart then it should be added to the cart | Pass | SH | Pass | CS - 11/3/2022
As an admin, I want to simplify the process to update product information so that name, price, and quantity can be updated individually. | Given a preexisting item when I try to change a property then I expect to be able to change each individually. | Pass | SH - in the admin detail menu | Pass | CS - 11/3/2022
As a customer, I want my cart to be saved so that I don't have to find products again. | Given I have used the site before when I log in then I should have my cart saved. |  |  | Pass | CS - 11/3/2022
As a customer, I want to visit a checkout page so that I can view the final price and purchase my items. | Given having items in the cart when I click the cart/checkout button then I will be led to a page displaying the total price and an option to buy. |  |  | Pass | CS - 11/3/2022
As a customer, I want to enter a valid discount code so that I can buy products for a cheaper price. | Given I have been given a discount code when I enter the code at checkout then the price of my cart/items should be at a discounted price. |  |  | Fail | CS - 11/3/2022 - not implemented | Pass | TL - 11/8/2022
As an admin, I want to enter discount codes so that a user can buy things at a cheaper price. | Given I input a discount code when I want to make a new code then the code should be saved. |  |  | Fail | CS - 11/3/2022 - not implemented | Pass | TL - 11/5/2022